## Slide 1: Software Project Management

## Slide 2: Organization of this Lecture:
Introduction to Project Planning
Software Cost Estimation
  Cost Estimation Models
  Software Size Metrics
  Empirical Estimation
  Heuristic Estimation
  COCOMO
Staffing Level Estimation
Effect of Schedule Compression on Cost

## Slide 3: Introduction
Many software projects fail:
  Due to faulty project management practices:
    It is important to learn different aspects of software project management.

## Slide 4: Introduction
Goal of software project management:
  Enable a group of engineers to work efficiently towards successful completion of a software project.
Consider management techniques required to
        plan
        organize
        monitor
        control

## Slide 5
What is software project management? ---the means of “management”
Any project with more than one person must be managed by definition
The job of management is to make sure that the planned junk does not get left behind in the zeal to release the software when only the program in its heart has been written!
  Allocate resources properly.
  Communicate and facilitate communication.
  Control leads to quality.
  Deliver what you promise.

## Slide 6
Effective SW project management focuses on 4 P’s:
People - the most important element of a successful project.
Product - the software to be built
Process - the set of framework activities and software engineering tasks to get the job done
Project - all work required to make the product a reality

## Slide 7
1. People
must be organized into effective teams
motivated to do high-quality work
coordinated to achieve effective communication and results

## Slide 8
2. Product (Problem)
must be communicated from customer to developer
decomposed into its parts
positioned for work by SW team

## Slide 9
3. Process
must be adapted to the people and problem to get the SW developed:
common process framework is selected
appropriate SWE paradigm is applied
set of work tasks chosen

## Slide 10
Project
  The objective of the project to build a program system product is to make sure that all the necessary junk gets planned in.
Projects have plans:
  Resources
    Multiple People
    Schedule
    Budget
    Others
  Specific work to do
  Deliverables
4. Project

## Slide 11: Responsibility of project managers
Project proposal writing,
Project cost estimation,
Scheduling,
Project staffing,
Project monitoring and control,
Software configuration management,
Risk management,
Managerial report writing and presentations, etc.

## Slide 12: Introduction
A project manager’s activities are varied.
  can be broadly classified into:
    project planning,
    project monitoring and control activities.
decide on process model
define preliminary plan based on process model
decompose process (add details to the plan)

## Slide 13
W5HH principle
Why is the system being develop?
  Answer to this questions help assess validity of business reason for the software work.
  It answers if the business purpose justifies the expenditure of people, time and money
What will be done?
  Answer to this question establishes the task set required for project
When will it be done?
  Answer to this question helps the team establish a project schedule by identifying when tasks have to be conducted and when milestones are to be reached

## Slide 14
W5HH principle (Contd.)
Who is responsible for a function ?
  Answer to this question establishes roles and responsibility of each team member
Where are they organizationally located ?
  Answer to this question indicates that all roles and responsibilities are not limited to the software team itself, the customers, users and stakeholders also have responsibilities.
How will be job done technically and managerially ?
  Once product scope is establishes, a technical and management strategy must be defined for it.
How much of each resource is needed ?
  Answer to this question is derived by developing estimates based on answers to earlier questions.

## Slide 15: Project Planning
Once a project is found to be feasible,
  project managers undertake project planning.

## Slide 16: Project Planning Activities
Estimation:
  Effort, cost, resource, and project duration
Project scheduling:
Staff organization:
  staffing plans
Risk handling:
  identification, analysis, and abatement procedures
Miscellaneous plans:
  quality assurance plan, configuration management plan, etc.

## Slide 17: Project planning
Requires utmost care and attention --- commitments to unrealistic time and resource estimates result in:
  irritating delays.
  customer dissatisfaction
  adverse affect on team morale
    poor quality work
  project failure.

## Slide 18: Sliding Window Planning
It is usually very difficult to make accurate plans for large projects at project initiation. A part of the difficulty arises from the fact that large projects may take several years to complete.
In order to overcome this problem, sometimes project managers undertake project planning over several stages.

## Slide 19: Sliding Window Planning (cont.)
Planning a project over a number of stages protects managers from making big commitments at the start of the project.
This technique of staggered planning is known as Sliding Window Planning.
(In this technique, starting with an initial plan, the project is planned more accurately over a number of stages.)

## Slide 20
Size Estimation
Effort Estimation
Cost Estimation
Duration Estimation
Staffing Estimation
Scheduling
Precedence ordering among
planning activities

## Slide 21: SPMP Document
After planning is complete:
  Document the plans:
  in a Software Project Management Plan(SPMP) document.
The controlling document for a software project.
Specifies the technical and managerial approaches to develop the software product.
Companion document to requirements analysis document: Changes in either may imply changes in the other document.
SPMP may be part of project agreement.

## Slide 22: Project Agreement
Document written for a client that defines
the scope, duration, cost and deliverables for the project,
the exact items, quantities, delivery dates, delivery location.
Can be a contract, a statement of work, a business plan, or a project charter.

## Slide 23: Organization of SPMP Document
  Introduction
  (Objectives, Major Functions, Performance Issues, Management and Technical Constraints)
  Project Estimates
  (Historical Data, Estimation Techniques, Effort, Cost, and Project Duration Estimates)
  Project Resources Plan
  (People, Hardware and Software, Special Resources)

## Slide 24: Organization of SPMP Document (cont.)
  Schedules
  (Work Breakdown Structure, Task Network, Gantt Chart Representation, PERT Chart Representation)
  Risk Management Plan
  (Risk Analysis, Risk Identification, Risk Estimation, Abatement Procedures)
  Project Tracking and Control Plan
  Miscellaneous Plans
  (Process Tailoring, Quality Assurance)

## Slide 25
Staffing
People are an organisation’s most important assets.
The tasks of a manager are essentially people-oriented. Unless there is some understanding of people, management will be unsuccessful.
Poor people management is an important contributor to project failure.

## Slide 26
Staffing ---Staffing Activities
Selecting Staffs
Organizing Teams
Managing Groups
Arranging Work Environment
Motivating People

## Slide 27
Staffing --- Selecting Staffs / Team Leader
The MOI Model:
  Motivation. The ability to encourage (by “push or pull”) technical people to produce to their best ability.
  Organization. The ability to mold existing processes (or invent new ones) that will enable the initial concept to be translated into a final product.
  Ideas or innovation. The ability to encourage people to create and feel creative even when they must work within bounds established for a particular software product or application.

## Slide 28
Staffing --- Organizing Teams/ Software Teams
The difficulty of the problem to be solved
The size of the resultant program(s) in lines of code or function points
The time that the team will stay together (team lifetime)
The degree to which the problem can be modularized
The required quality and reliability of the system to be built
The rigidity of the delivery date
The degree of sociability (communication) required for the project
The following factors must be considered when selecting a software project team structure ...

## Slide 29
The physical workplace provision has an important effect on individual productivity and satisfaction
  Room size
  Furniture
  Equipment
  Temperature
  Humidity
  Brightness
  Noise
  …
Staffing --- Working environments

## Slide 30
Staffing ---Motivating People
An important role of a manager is to motivate the people working on a project.
Motivation is a complex issue but it appears that their are different types of motivation factors
People go to work because they are motivated by the people that they work with.

## Slide 31
Staffing ---Managing groups
Most software engineering is a group activity
  The development schedule for most non-trivial software projects is such that they cannot be completed by one person working alone.
“Schedule disaster, functional misfit and system bugs all arise because the left hand does not know what the right hand is doing”
Teams working on a project must communicate with one another in as many ways as possible: informally, regular project meetings email and by a shared project (electronic) workbook.

## Slide 32
Scheduling
One of the most important things you
can do is schedule.
Also one of the first things you should do!
Tools help
  Microsoft Project
  OpenProj.org
  OpenWorkbench.org